## Slide 1: 3rd Information session TR2021 - Tranche 1
Programme Allocatie 2.0

## Slide 2: Agenda
Opening Mirjam van der Horst, Vz SR NEDU, secretary SSG
Qualification MMC Hub TenneT Elderik de Witte, project manager TenneT
General test planning
Lead group tests
User Acceptance Tests (GAT) (groups)
Jorik van Vilsteren, Test and Transition manager EDSN and NEDU
Transition go live and inflow MRP parties dual phase Anton de Beij, Transition coordinator, EDSN and NEDU
Update Requests for Change (RFC’s) Bram van Straalen, DSO expert
Programme Allocatie 2.0 on mijnNEDU
Mirjam van der Horst, Vz SR NEDU, secretary SSG
Wrap-up

## Slide 3
Qualification MMC Hub TenneT
Elderik de Witte - Project manager Allocatie 2.0 TenneT

## Slide 4: Qualification MMC Hub in 2 steps
Establishing connection
Information can be found in document: Test and Qualification Guide on mijnNEDU (Releases/TR2021 – tranche 1 A2.0/Tests/Tests MMC hub)
Qualification
Questions: allocatie2@tennet.eu
Questions: allocatie2@tennet.eu
TQF environment
TQF environment
Information in Qualification plan on mijnNEDU (Releases/TR2021 – tranche 1 A2.0/Tests)

## Slide 5
Nov‘21
Dec‘21
Jan '22
Feb '22
Mar ‘22
Apr ‘22
Timeline
Qualification for Measurements (TQF)
17 Dec ’21
3 Jan ’22
19 Mar ’22
Timeline qualification
Go-live/Dual phase (PROD)
NEDU GAT (Q)
May ‘22
Jun ‘22
Qualification (TQF)

## Slide 6: Qualification support
We try to respond to e-mails within 1 day
However, due to sick leave, this cannot be guaranteed at the moment
We are trying to resolve this situation as quickly as possible

## Slide 7: Interaction with go live E-programme project
Reminder for BRPs that may be late in implementing TR2021. As of the TR2021 go-live, allocation - for connections that have made the switch - can only be appealed using the new XML appeal messages. The route via grid operators will no longer be valid. So make sure that these appeals are implemented and qualified in good time
On 18 November, TenneT announced that it expected the E-programme project to go live in January 2022, and be followed by a phased transition (pilot, only international parties, domestic and international parties)
BRP’s that only operate at domestic level have (almost) all been qualified. That is why there will be no interference between the E-programme project and Tranche 1 Allocatie 2.0 (Qualification and NEDU GAT) during testing
There is a risk of the transition period for the E-programme - for BRP’s that only operate at domestic level - overlapping with the go live for Tranche 1 Allocatie 2.0 on 19 March 2022
Do you have comments or are you unable to comply with the requirements above? Then please contact us via EDIXML@tennet.eu, so that the TenneT EDIXML programme can deal with them in advance

## Slide 8
General test planning, Lead groups tests, User Acceptance Tests (GAT) (groups)
Jorik van Vilsteren - Test and Transition manager, EDSN and NEDU

## Slide 9: Test planning Tranche 1 Allocatie 2.0
WGA – Premature Acceptance
T2: GAT
3 Jan. ’22
Go Live
19 Mar. ’22
T2’: FAT/K
29 Nov. ‘21
Deployment
Transition & Go Live
After care
Management
PI-21.4
PI-22.1
PI-22.2
Q1 ‘21
Q2 ‘21
Q3 '21
Q4 '21
Q1 ‘22
Q2 ‘22
Program Incr.
Quarter
NEDU
EDSN
Int. MMC-hub
April ’21
TEST
GAT
End RNBAT
26 Nov. ’21
1
2
6
7
8
Design, Construction and Testing
Design, Construction and Testing
Acceptance
Transition
PI-21.3
PI-21.1
Phase 4 |
Acceptance Market
Phase 1 | Acceptance User Stories
Phase 2 | Acceptance Features
Phase 3 |
Acc. Epics
Start Phase 3
1 Aug. ’21
Scrum Test – Unit Test, FAT, Regression Test, ART
Management Test – Performance, Security
3
# | Activity | Start | End
 | Sanity Check (SC) TRAN | 26 July ’21 | 30 July ‘21
 | Intake Test (IT) TRAN | 2 Aug. ‘21 | 13 Aug. ’21
 | Sanity Check (SC) ACT2 | 6 Sept. ‘21 | 10 Sept. ’21
 | Intake Test (IT) ACT2 | 13 Sept. ‘21 | 24 Sept. ’21
 | Management Acceptance Test (BAT) | 16 Aug. ‘21 | 26 Nov. ’21
 | RNB Acceptance Test (RNBAT) | 16 Aug. ‘21 | 26 Nov. ’21
 | Funct. Acceptance Test - Lead group (FAT-K) | 29 Nov. ‘21 | 17 Dec. ’22
 | GAT | 3 Jan. ’22 | 25 Feb. ’22
 | Go Live | 19 Mar. ’22 | 
SC
RNBAT
3
3
5
BAT
IT
4
5
6
7
8
PI-21.2
Integration Test
FAT-K
4
4
TODAY

## Slide 10: Lead group tests (1)
Start date Lead group tests: 29 November 2021
End date Lead group tests: 17 December 2021
Lead group consists of:
  Kenter (MRP)
  PVNED (BRP)
  Gasunie Transport Services (TSO-G)
  TenneT TSO (TSO-E)
  Eneco (SUP)
  Essent (SUP)
  Liander (DSO)
  Stedin (DSO)
  Enexis (DSO)

## Slide 11: Lead group tests (2)
Test scope:
  Progression tests and
  Regression tests
Determined using a pre-agreed set of test scenarios
End result:
  Advice to release the environment for the next test phase in the project, namely the User Acceptance Test (GAT)
Finally:
  Market parties that participate in the Lead group will voluntarily contribute to the successful implementation of Tranche 1 of Allocatie 2.0. I would hereby like to thank Alex, Abel, Erik, Remco, Kemal, Ivo, Nico, Rudolf, Dennis, Daniel and Steve for their contributions thus far, and their work is one of the reasons why I am positive about the rest of the Tranche 1 process

## Slide 12: User Acceptance Test (GAT) (1)
Test scope:
  Free testing
End result:
  An advice to start the transition based on pre-agreed criteria
Start date GAT group 1: 03 January 2022
End date GAT group 6: 28 January 2022
Overrun/re-test: 31 January to 25 February 2022
Freeze: 28 February to 18 March 2022

## Slide 13: User Acceptance Test (GAT) (2)
GROUPS
Provisional

## Slide 14
Start date: 03 January 2022
End date: 07 January 2022
Kick-Off: 3 January 9 am
Interim Update: 5 January 9 am
Final Update: 7 January 9 am
GAT group 1

## Slide 15
Start date: 10 January 2022
End date: 14 January 2022
Kick-Off: 10 January 9 am
Interim Update: 12 January 9 am
Final Update: 14 January 9 am
GAT group 2
Market party | Market role
Tennet TSO | TSO-E
Energie Consult Holland | MRP
Fudura B.V. | MRP
RWE MV | MRP
Enexis | BRP/SO
Danske Commodities A/S | BRP
EnergiePlaza B.V. | BRP
ENGIE Energie Nederland N.V. | BRP
Gasela SHIPPER | BRP
Wintershall Holding GmbH | BRP
Energy Trading Company B.V. | BRP
FENOR B.V. | BRP
Groene Energie Administratie B.V. | BRP
NutsServices B.V. | BRP
Shell Energy Europe Limited | BRP
Essent SPMGas | BRP
RWE Supply & Trading Netherlands B.V. | BRP
Koch Supply and Trading SARL PV | BRP
Orsted Salg & Services A/s | BRP
Sunnic Lighthouse GmbH | BRP

## Slide 16
Start date: 10 January 2022
End date: 14 January 2022
Kick-Off: 10 January 1 pm
Interim Update: 12 January 1 pm
Final Update: 14 January 1 pm
GAT group 3
Market party | Market role
Tennet TSO | TSO-E
Ealyze B.V. | MRP
DNWG Infra B.V. | MRP
Enduris | BRP/SO
Stedin | BRP/SO
DC Energy Trading B.V. | BRP
Energie E&E B.V. | BRP
Eni S.p.A. | BRP
GasTerra B.V. | BRP
In Commodities A/S | BRP
PVNED | BRP
Total Gas & Power Nederland B.V. | BRP
Xenon Capital Markets Limited | BRP
VNG Handel & Vertrieb GmbH | BRP
Yuso BVBA | BRP
Norsk Hydro Energy PV/SH | BRP

## Slide 17
Start date: 17 January 2022
End date: 21 January 2022
Kick-Off: 17 January 9 am
Interim Update: 19 January 9 am
Final Update: 21 January 9 am
GAT group 4

## Slide 18
Start date: 17 January 2022
End date: 21 January 2022
Kick-Off: 17 January 1 pm
Interim Update: 19 January 1 pm
Final Update: 21 January 1 pm
GAT group 5

## Slide 19
Start date: 24 January 2022
End date: 28 January 2022
Kick-Off: 24 January 9 am
Interim Update: 26 January 9 am
Final Update: 28 January 9 am
GAT group 6

## Slide 20: User Acceptance Test (GAT) (3)
The lead time for the GAT, under central management of NEDU, amounts to 1 week
In order to start the GAT, market parties must first have qualified with Tennet TSO
During this week, dedicated support will be offered by EDSN and TenneT TSO in order to resolve findings and other obstacles for a successful GAT
Monday kick-off with GAT group, Wednesday update meeting with GAT group, Friday finishing call with GAT group
Market parties that are absent during the kick-off will be contacted, using the e-mail address registered with NEDU, to still take part in the GAT. If a market party is absent for the 2nd time on Wednesday, NEDU will assume that the concerned party will not be participating in the GAT and its market readiness will then be set to ‘yes’. There will be a wrap-up session on Friday
Findings will be presented to the submitting party for re-testing. If this is not possible, another market party with the same market role will be approached
Apart from the week of the GAT, market parties are free to test against the central system. Please note: management departments at EDSN and TenneT TSO will prioritise NEDU GAT groups that are active at that moment in time
The GAT will be carried out on the CAR ACT, CARM ACT2 environment. Tennet TSO will mention before 1 December whether this involves the MMC HUB T3 environment.
Do you have questions about the provisional groups? Send an e-mail to allocatie2.0@edsn.nl

## Slide 21
Transition go live and inflow MRP parties dual phase
Anton de Beij - Transition coordinator, EDSN and NEDU

## Slide 22: Planning transition
Appendix: Planning scripts TR2021 - Tranche 1 Allocatie 2.0
August
September
October
March
February
January
December
November
Preparation
Focus points and lessons learned
Development general outline for Transition per market role
Development Script EDSN / NEDU Inflow MRP’s (Dual phase)
Preparation communication Transition
Technical
Dry run
Preparation Technical Dry run
DR2
April
May
Process and
Technical
Dry run
Evaluation and preparation Process and Technical Dry run
Develop Roll back and Fall back
Go Live
Preparation Go Live
Overseeing inflow MRP’s into Dual Phase
End
dual phase*
DR3
GL
Execution Communication Transition
* Removal of old functionality after dual phase is optional; no central activities for the time being
Dual phase
Process and
Technical
Dry run
Development Script EDSN / NEDU
(Deployment weekend 19 Mar)
DR1
Evaluation Process and Technical Dry run

## Slide 23: Preparation go live
Relates to go live on Saturday 19 March 2022 (EDSN, TenneT, GTS, BRP parties and DSO’s)
Compile Central Transition Script (incl. coordination with TenneT)
Review Central Transition script by Advisory Group (KBG) Transition
Preparation roll- and fallback plan
Technical dry-run by EDSN and TenneT start of January 2022
Process-related and technical dry-run EDSN, TenneT and DSO’s start of March 2022
Evaluation for both dry-runs to prepare for go live
After-care plan currently being compiled
Communication in preparation
The dual phase for Inflow MRP parties will start after the go live

## Slide 24: Preparation inflow MRP parties dual phase
Central Transition Script has been compiled and review has been carried out by KBG Transition
Preparation dry-run:
  Participation by Kenter, TenneT, GTS, PVNED, Stedin and EDSN
  Test cases compiled for Production Acceptance Test (PAT). During the PAT, a check will be carried out to see if the system landscape of the MRP is operational in the production environment. This will be assessed by exchanging several messages with BRP, DSO and TSO
  During the dry-run, the Transition script will be carried out in exactly the same manner as the actual MRP inflow
  The dry-run will take place on Monday 6 December 2021
After the dry-run, an evaluation with stakeholders will take place to prepare for the go live
Communication in preparation (by TenneT and NEDU)
After-care plan in preparation

## Slide 25: Planning inflow MRP parties dual phase
Request MRP parties to indicate the day on which they want to flow in, so that planning can be completed and pairs can be formed for the PAT
Inflow possible on days that have not been crossed out Friday 13-5-2022 is the last available day if previous inflow was unsuccessful (initial PAT not completed successfully)
First come, first served
MRP parties should register as soon as possible via e-mail: allocatie2.0@edsn.nl

## Slide 26
Update Requests for Change (RFC’s)
Bram van Straalen - DSO expert

## Slide 27: RFC’s since previous information session (red = new)
Contents
  RFC TR2021.1 ‘BRS update van versie 1.0 naar 2.0’
  RFC TR2021.3 ‘Aanpassing BD MeasurementSeriesAcknowledgement’
  RFC TR2021.4 ‘BRS update van versie 2.0 naar 3.0’
  RFC TR2021.5 ‘Technische validaties Allocatie 2.0 berichtenverkeer’
  RFC TR2021.6 [Not submitted and not approved]
  RFC TR2021.7 Sender and receiver entities
  RFC 249.1 ‘Splitsen verbruiken bij PV-Switch’
  RFC 249.2 ‘Mapping XML Meetwaarden telemetrie met MSCONS 99E’
  RFC 249.3 ‘Mapping statuscodes van XML Meetwaarden telemetrie naar BALL’
  RFC 249.4 ‘Tijdigheid maandelijkse bericht tijdseries ELK‘
  RFC 249.5 ‘Toevoegen Use-cases LNB-E’
  RFC 249.6 Market role in BD VolumeSeriesNotification
  RFC 231.1 ‘Handmatige acties RNB op niet-werkdagen’
Scope
  RFC TR2021.2 ‘Uitbreiden scope met IC259’
  RFC ‘Scopewijziging TR2021 door IC270’
A few service descriptions and message definitions have also changed as a result. The latest versions can be found on mijnNEDU

## Slide 28
Programme Allocatie 2.0 on mijnNEDU
Mirjam van der Horst - project manager NEDU, chairman SR NEDU and secretary SSG

## Slide 29: Programme Allocatie 2.0 on mijnNEDU
All approve documents for the programme (not the tranches) can be found at ‘Programme Allocatie 2.0’, such as:
  organisation of the programme
  scope and implementation strategy
  planning
  public justification
  main story for the programme (brief explanation about why, how and what for Allocatie 2.0)

## Slide 30
Questions?

## Slide 31
Thank you for your attention